## Sheet1
CCIM Working Group - Project Status Update - 08-07-2020
Project # | Funded? | Project | Notes | Plan Phase | Planned Construction Year | Current Phase | Total Cost | Funding Sources
1 | YES | Burnside: Phase I - bridge deck | eastbound bus lane on bridge | Years 1-5 | 2019 | Complete | 100000 | ETC
5 | YES | SW Madison bus lane | bus lane, protected bike lane | Years 1-5 | 2019 | Complete | 160000 | ETC
7 | YES | Everett bus lane | bus lane | Years 1-5 | 2019 | Complete | 1020000 | ETC
1 | YES | Burnside: Phase II - MLK to 12th | eastbound bus lane, rebuild signal with protected phase at MLK | Years 1-5 | 2020 | Final Design | 1660000 | ETC
2 | YES | SW 4th: Phase I & 2 | Paving, bus lane, signals, street lights, NB protected bikeway | Years 1-5 | 2021/22 | Refining Concept Design | 17361384.6144 | FOS, SSL, TDSC, TriMet ETC, Prosper Portland
3 | YES | Grand bus lane | transit lane | Years 1-5 | Summer 2020 | Final Design | 901816 | CMAQ Funds Transfer
6 | YES | SW 17th: Salmon to Burnside | bike connection through Goose Hollow | Years 6-10 | 2020 | 30% Design | 270934 | FOS
15 | YES | NE Lloyd & Sullivans Bridge connections | two-way cycletrack connecting RQ, Sullivans | Years 1-5 | 2020 | Tied to Bridge project | 2000000 | TSDCs
17 | YES | Better Naito Forever | two-way cycletrack, signal upgrades, sidewalk infill | Years 1-5 | 2020 | Final Design | 4958228 | FOS, GTR, TSDCs
12 | YES | SE Hawthorne: Bridge to 12th | protected bike lane, transit priority, bus islands | Years 1-5 | Fall 2020 | 95% Design | 1169736 | CMAQ Funds Transfer, TSDCs
3 | YES | MLK bus lane | transit lane | Years 6-10 | Fall 2020 | Final Design | 906690 | CMAQ Funds Transfer
5 | YES | Collins Circle | protected bike lane, transit priority on SW Jefferson between 14th and 18th | Years 1-5 | 2021 | Design | 75000 | PBOT, TriMet STIF Funds
2 | YES | SW / NW Broadway Phase I | Phase I protected bikelanes on Broadway, ETC on NW Broadway | Years 1-5 | Oct. 2020 | Construction | 1964870 | CMAQ Funds Transfer
13 | PENDING T2020 | NE Multnomah | upgrade exisiting streetscape, bus islands | Years 1-5 | TBD |  | 7164000 | GoLloyd, TSDCs, T2020 CCIM
6 | PENDING T2020 | NW 14th Ave: Burnside to Naito | crossing, ADA and bicycle facility upgrades | Years 1-5 | TBD |  | 1513583 | T2020: CCIM
2 | PENDING T2020 | Broadway: Phase II - Burnside to Caruthers | southbound protected bikeway | Years 1-5 | TBD |  | 10166000 | T2020: CCIM
2 | PENDING T2020 | NW 4th: Phase III - Burnside to Flanders | NB bike connection to Flanders | Years 1-5 | TBD |  | 94899 | T2020: CCIM
3 | PENDING T2020 | NE/SE 7th Ave | protected bikeway | Years 1-5 | TBD |  | 8361000 | T2020: CCIM
8 | PENDING T2020 | SW Salmon / Taylor | create new major E/W bicycle connection through downtown | Years 1-5 | TBD |  | 8778000 | T2020: CCIM
14 | PENDING T2020 | SE Water | two-way cycletrack | Years 6-10 | TBD |  | 4132000 | T2020: CCIM
1 | PENDING T2020 | Burnside: Phase III - Park to 2nd | eastbound bus lane, crossing upgrades, bike connections | Years 1-5 | TBD |  | 4114000 | T2020: CCIM
2 | PENDING T2020 | SW College | Green Loop connection | Years 1-5 | TBD |  | 232921 | T2020: CCIM
6 | PENDING T2020 | SW 12th Ave: I-405 to Stark | protected bike lane | Years 6-10 | TBD |  | 1051823 | T2020: CCIM
12 | PENDING T2020 | SE Madison | bus priority, new signal at 12th | Years 6-10 | TBD |  | 1861975 | T2020: CCIM
5 | PENDING T2020 | SW Jefferson/Columbia | transit priority improvements for this major bus corridor | Years 6-10 | TBD |  | 6553000 | T2020: CCIM
18 | PENDING T2020 | NE Broadway | safety improvements in partnership with Albina Vision | Years 6-10 | TBD |  | 2500000 | T2020: Albina Vision
18 | PENDING T2020 | NE Weidler | safety improvements in partnership with Albina Vision | Years 6-10 | TBD |  | 2500000 | T2020: Albina Vision
9 | NO | SE Salmon | greenway connection to espenade | Years 1-5 |  |  | 493000
11 | NO | SE Belmont / Morrison | bus lane, protected bikeway couplet | Years 6-10 |  |  | 6000000
10 | NO | SW Alder | bikeway connection to Morrison Bridge | Years 6-10 |  |  | 1324000
16 | NO | NW 9th Ave, Park | bike connections thru Pearl | Years 6-10 |  |  | 4398000
4 | NO | 11th/12th: Division to Sandy | pedestrian crossing, freight and bicycle improvements | Years 6-10 |  |  | 4696756.5767
4 | NO | 12th: Sandy to I-84 | pedestrian crossing, freight and bicycle improvements | Years 6-10 |  |  | 2742243.4233
12 | NO | SE Clay | bikeway connection to Hawthorne Bridge | Years 6-10 |  |  | 1199983
|  |  | TOTALS |  |  |  | 112425842.6144
ETC = TriMet Enhanced Transit Corridors, FOS = PBOT Fixing Our Streets gas tax, SSL = Signals Maintenance, TDSCs = Transportation System Development Charges
CMAQ = Congestion Mitigation and Air Quality federal grant funds, RRFA = Metro Regional Flexible Funds grant program, STIF = Federal Funds through TriMet
T2020 = Metro's Get Moving transportation funding intiative