## 100%
Senior Engineer Final PS&E Checklist
Project Number: |  | Date of Review:
Senior Engineer:
Checked (Yes,No, or N/A) | Checklist Item | Category | Comments
| 30%, 60%, 95% and 100% Design Checklists are completed and confirmed. | Checklists
| Drafting Checklist completed and confirmed. | Checklists
| ROW, TCE’s, and permanent easements acquired. Private Property impacts identified and resolved in PS&E. | ROW
| Environmental report reviewed, implemented, and in Special Provisions appendix. | Special Provisions
| Pavement Design Report Finalized, implemented, and in Special Provisions appendix | Special Provisions
| Geotechnical Report finalized, implemented, and in Special Provisions appendix. | Special Provisions
| Urban Forestry Permit acquired and in Special Provisions Appendix | Special Provisions
| Design exceptions approved. | Special Provisions
| ADA Ramp Reports approved. All variances and MEF's in Special Provisions appendix and provided to ADA Ramp Crew. | Special Provisions
| PS&E review comments addressed satisfactorily, and responses/resolutions logged accordingly. | General
| Noise Variance acquired( if Night Work Required) and in Special Provisions appendix | Special Provisions
|  Utility Notifications (1st, 2nd and 3rd utility notifications issued.) | Utility
| Utility Relocation Demand Letters Sent. | Utility
| All required permits acquired, including ODOT permits and Railroad permits. All permits included in Special Provisions appendix | Special Provisions
| Confirm completion date given in Special Provisions is reasonable | Special Provisions
| Confirm that all ped push button locations and signal elements are coordinate with ramp/landing locations – proper height, clearance, no obstructions, etc. | Plans
| Confirm that earthwork quantities have been calculated per 00330. | Estimate
| Confirm final estimate bid item names and units are in agreement in Plans, Specs, and Estimate. | Estimate
| Review PEER Review findings and confirm that all issues addressed. | General
| Confirm Consultant has delivered all required items - for example QC Verification Letters on file,electronic design files, quantitiy calculations | General
| Confirm Final Estimate(with contingency) and Construction Engineering Estimate are within project budget | General
| In-House Design, Design DTM's have been reviewed for the following: Earthwork quantity calculations have been confirmed , grading limits are accurate and consistent between plans and DTM, and DTM shows good drainage practices. | Design Files